Sprint 4 Planning Document

For the Girl Scouts of America Badge Tracking Application

By

Matt Eck

Michael Glosecki

Nathan Martz

Ryan Schroeder

Of Team Cookie Council

**Sprint planning document for sprint 4**

|  |
| --- |
| **GOAL:** To complete basic HTML pages with database interactions using PHP, and to begin development on the mobile application prototype. |

* Complete refinement of basic HTML pages (20ph)
* Create Additional HTML pages(10ph)
* Add database interactions to HTML pages using PHP (20ph)
* Test HTML / database interactions (10ph)
* Begin Mobile application prototype(30ph)

All stories on product backlog

**\*Hours will be deducted from the backlog then Re-Factored**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Week 1 Tasks** | **Mon 11/9** | **Tue 11/10** | **Wed 11/11** | **Thu 11/12** | **Fri 11/13** | **Sat 11/14** | **Sun 11/15** | **Work Remaining** |
| **HTML Refinement** |  |  |  |  |  |  |  | 0 |
| * Nate | 2 | 3 | 3 | 3 |  |  |  | 11 |
| * Mike | 1 | 3 | 2 | 3 |  |  |  | 9 |
| **Additional HTML** |  |  |  |  |  |  |  | 0 |
| * Nate |  |  |  | 2 | 2 |  |  | 4 |
| * Mike |  |  |  | 1 | 2 | 3 |  | 6 |
| **Database Interactions** |  |  |  |  |  |  |  | 12 |
| * Matt |  |  |  | 1 |  | 1 |  | 2 |
| * Mike |  |  |  |  | 1 | 1 |  | 2 |
| * Nate |  |  |  |  | 2 |  |  | 2 |
| * Ryan |  |  |  | 1 | 1 |  |  | 2 |
| **Mobile Application** |  |  |  |  |  |  |  | 16 |
| * Matt | 2 | 2 |  | 2 | 1 |  |  | 7 |
| * Ryan | 2 | 1 | 1 | 1 | 1 | 1 |  | 7 |
| **Total** | 8 | 9 | 6 | 13 | 10 | 6 |  | 52 |

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Week 2 Tasks** | **Mon 11/16** | **Tue 11/17** | **Wed 11/18** | **Thu 11/19** | **Fri 11/20** | **Sat 11/21** | **Sun 11/22** | **Work Remaining** |
| **Database Interactions** |  |  |  |  |  |  |  | 0 |
| * Matt | 1 | 2 |  |  |  |  |  | 3 |
| * Mike |  | 2 | 1 |  |  |  |  | 3 |
| * Nate |  | 2 | 1 |  |  |  |  | 3 |
| * Ryan |  | 2 |  | 1 |  |  |  | 3 |
| **HTML Testing** |  |  |  |  |  |  |  | 0 |
| * Matt |  |  |  | 1 | 1.5 |  |  | 2.5 |
| * Mike |  |  |  | 1 |  |  | 1.5 | 2.5 |
| * Nate |  |  |  | 1 | 1.5 |  |  | 2.5 |
| * Ryan |  |  |  | 1 |  | 1.5 |  | 2.5 |
| **Mobile Development** |  |  |  |  |  |  |  | 0 |
| * Matt | 2 | 2 | 1 | 2 | 1 |  |  | 8 |
| * Ryan | 2 | 2 |  | 2 | 1 | 1 |  | 8 |
| **Total** | 1 | 12 | 2 | 9 | 4 | 2.5 | 1.5 | 32 |